Proposal Checklist

Interdisciplinary Research Grant for Convergent Innovation

Submission Deadline: Monday, October 6, 2025, 9:00AM EST

- Project Summary

- Signature Page

- Project Description

- References and Citations

- Statement of Interdisciplinary Collaboration

- 2-page CV/biosketch

- Budget

- Budget Justification

- List of Current and Pending Support

- List of Future Funding Prospects

- Convert application materials into a single PDF for submission via the online system

File name: IRG2025_LastNameofLeadPI_proposal.pdf

File name: IRG2025_Smith_proposal.pdf

# Project Summary

Participating Faculty

1. Lead PI

Name:  	David B Smith	Department: 	Entertainment Technology

Rank: 	Professor	College:	City Tech

2. Co-PI

Name: 	Ann Delilkan	Department: 	Humanities

Rank:	Associate Professor	College:	City Tech

3. Co-PI

Name: 	Michael Lipsky	Department: 	Aaron Copland School of Music

Rank:	Professor	College:	Queens College

4. Co-PI

Name: 	Christopher Swift	Department: 	Humanities

Rank:	Professor	College:	City Tech

Project Title:

Holistic Integration as Convergent Innovation: Blended Shadow Puppetry, Gamelan, and Collaborative AI

Summary: Interdisciplinary research thrives when diverse perspectives converge to address pressing concerns. The Center for Holistic Integration (CHI) extends this principle through its model of meta-projects that unite all disciplines—artistic, scientific, and humanistic—within a shared ecosystem of research and creativity. The critical social issue our proposal addresses is this: How can humanity live and work with machine intelligence without sacrificing its humanness?

In this proposal, CHI joins forces with Queens College’s Gamelan Yowana Sari to integrate gamelan (traditional Indonesian music) and wayang kulit (traditional shadow puppetry)—both UNESCO Intangible Cultural Heritages — with immersive technologies and machine intelligence through our continuing Blended Shadow Puppet (BSP) meta-project. In doing so, we honor historical practices while embracing modern tools.

Our efforts will generate broad public impact through cultural popup performances; integration of gamelan musicians into the ongoing shadow puppet meta-project; and the development of K-12 outreach resources. This unique partnership demonstrates how cultural heritage can serve as a living laboratory—advancing Collaborative AI; producing new frameworks for human–machine creativity; and establishing a scalable foundation for future interdisciplinary research and collaboration, while generating creative and scholarly output across multiple fields, including performance, technology, cultural studies, and design.

# Signature Page

Title of Proposal: Holistic Integration as Convergent Innovation: Blended Shadow Puppetry, Gamelan, and Collaborative AI

(Please insert additional signature lines as necessary)

Faculty Signatures

Name:      	Signature:					Date:

Name:      	Signature:					Date:

Name:      	Signature:					Date:

Name:      	Signature:					Date:

Signature of Grants Officer

Name:      	Signature:					Date:

Campus endorsement if requesting salary support (department chair or provost): This is to certify that the applicant from this college is authorized to conduct the study described in this proposal, and the undersigned is satisfied that the scope of the applicant’s project will not interfere with his or her professional duties.

Signature: 							Date:

Title:  								College:

Signature: 							Date:

Title:  								College:

## OVERVIEW

This proposal seeks support from the CUNY Interdisciplinary Research Grant (IRG) for a collaboration between the Center for Holistic Integration (CHI) at City Tech and Gamelan Yowana Sari at the Aaron Copland School of Music, Queens College. The project expands upon CHI’s Blended Shadow Puppet (BSP) initiative, creating a laboratory where cultural heritage and technological innovation meet. By bringing gamelan and wayang kulit into conversation with AI, the project investigates how traditions can adapt without losing authenticity, while testing new models of human–machine collaboration.

The stakes are both technological and cultural. As the Social Construction of Technology (SCOT) framework reminds us, technology does not evolve inevitably but is shaped by social groups, institutions, and negotiated choices. By situating cultural heritage at the center of this negotiation, the project ensures that traditions are not displaced but instead help to shape future technologies. This approach aligns directly with IRG’s emphasis on convergent innovation: interdisciplinary teams addressing urgent societal concerns.

The performance laboratory model demonstrates ways that cognitive and computational intelligence can work together. AI can be used to enhance or modify different parts of a blended environment, supporting rather than replacing creativity. Gamelan and wayang kulit, both UNESCO-listed traditions, are also living art forms, evolving through media, intercultural work, and new compositions. Recent productions in this genre have included stories from Star Wars, for example. Extending these same approaches within CHI’s framework demonstrates how heritage practices can shape modern performance and technology, deepening our connection to cultural roots, while using local themes, tropes and other communicative forms to expand this genre in new and innocvative directions.

Outcomes include public-facing performances, scholarly and creative product, innovative techniques in blended theatre, and a tested interdisciplinary infrastructure linking students and faculty from all disciplines across CUNY. This integration offers a generalizable model for understanding and describing how cultural traditions worldwide can navigate technological change while preserving vitality.

### CHI Philosophy and Alignment with IRG

The Center for Holistic Integration (CHI) is built on the recognition that, while interdisciplinary research is powerful, it is also bounded: Often, a particular initiative, such as STEM, explicitly combines a fixed set of disciplines, while leaving others outside its frame. CHI flips this approach by treating integration itself as the goal. Instead of defining boundaries, CHI creates large-scale meta-projects that welcome participation across every discipline and institution, ensuring that a philosopher, engineer, musician, or business student can each find meaningful ways to contribute to the same collaborative work. CHI also provides the connective infrastructure—shared frameworks, project scaffolding, and cross-disciplinary pathways—that organizes diverse contributions into coherent, sustainable platforms of innovation. Holistic Integration is thus not a single project but an organizing principle, aligning directly with the IRG’s priorities: fostering convergent innovation, generating public impact, producing new knowledge and methods, and preparing teams for larger external funding opportunities.

## 1. PUBLIC IMPACT

The collaboration will generate significant public benefit by uniting cultural heritage, technology, and community engagement. It directly meets the IRG requirement for impactful outcomes in cultural participation, creative innovation, and educational access.

Integrated Public Performances: Two integrated public performances will anchor the project’s outreach. The first, within a cultural popup event, will feature Gamelan Yowana Sari in traditional formation, accompanied by a shadow puppet performance projected above the ensemble. The second will present a modern blended environment in which gamelan interacts with a collaborative team of living and virtual artists within immersive technologies, maintaining cultural authenticity while exploring new collaborative possibilities. These performances collectively demonstrate how traditional music and puppetry can evolve through interaction with AI and digital media.

Blended Performance Development: The project will refine methods for integrating physical, digital, and intelligent agents in performance. Experiments with collaborative AI will provide real-world examples of human–machine partnership in the performing arts, testing possible methods of collaboration and contributing new approaches to both creative production and applied research.

Education and Community Engagement Planning: This phase of the project will focus on designing and planning future educational outreach. The team will develop a portable, easily deployed workshop package that can be implemented in later funding cycles. The proposed materials will outline how K–12 and community programs could introduce students and audiences to both traditional and blended performance forms. Documentation and recorded materials from this grant will support the creation of this outreach framework, ensuring its adaptability for future deployment.

Public Benefit: The collaboration invites audiences to experience UNESCO-recognized traditions in dynamic, evolving contexts. By demonstrating how cultural preservation, technological innovation, and collaborative AI can coexist within blended performance, it builds cultural awareness, advances technological literacy, and models human–machine collaboration as a creative and socially relevant practice.

## 2. COLLABORATION AND CONVERGENT INNOVATION

This proposal, if funded, will support the integration of two established ensembles with proven track records into a larger investigative framework: the Gamelan Yowana Sari ensemble and the Blended Shadow Puppet Theatre. Rather than creating a new collaboration from scratch, the project builds upon existing infrastructures and creative outputs, directing resources toward their meaningful integration.

Convergent innovation lies at the core of CHI’s philosophy. By structuring research around meta-projects that connect diverse disciplines and traditions, CHI transforms interdisciplinarity from a set of collaborations into a living system of continuous integration and mutual discovery.

At City Tech, the research team brings deep competencies in immersive environments, human–machine collaboration, AI integration, and technology-driven performance systems. At Queens College, the Gamelan Yowana Sari ensemble contributes expertise in performance, ethnomusicology, and living cultural practice. The collaboration will also involve scholars from the CUNY Graduate Center as well as invited experts—puppeteers, composers, technologists, and cultural historians—ensuring both technical rigor and cultural authenticity.

This structure is designed to produce convergent innovation in practice: new models where cultural heritage and advanced technology evolve together. The team will explore collaboration between human and machine intelligence and investigate the dynamic balance between tradition and innovation in living art forms. Beyond performances, the project advances understanding of communication in combinative reality; develops methodologies for AI collaboration; and establishes frameworks for adaptive cultural preservation that honor continuity of tradition while enabling creative evolution.

## 3. KNOWLEDGE AND OUTCOMES

This collaboration will generate knowledge across a variety of domains, including artistic, technological, cultural, and educational. Using performance as both the site and method of inquiry, our integration of Gamelan Yowana Sari and the Blended Shadow Puppet (BSP) transforms performance into a research instrument—one designed to produce both tangible and theoretical outcomes.

### 3.1. Research Deliverables

The project will yield new data and frameworks on human–machine collaboration through live blended performance. Each rehearsal, performance, and recording becomes a test environment for studying the interaction between human musicians, puppeteers, and intelligent systems. Findings will directly inform ongoing refinement of CHI’s Balanced Blended Space (BBS) framework System, advancing models of communication and mediation across physical, virtual, and conceptual spaces.

Deliverables also include the development of new technologies and techniques for use in blended performance and immersive environments, as well as studies identifying best practices for human–machine collaboration. These outcomes will enhance not only artistic production but also pedagogy and applied research in human–AI interaction.

The work connects to, and benefits from, CHI’s wider research ecosystem. Other CHI teams are investigating Collaborative AI in media delivery, puppet automation, AI-controlled drone behavior, and bio-awareness. Parallel explorations across other meta-projects—including the UNESCO Heritage and Fictive World Integration initiatives—contribute to a shared repository of data, techniques, and analysis that continually enriches collective outcomes.

### 3.2. Cultural and Educational Outcomes

The Spring 2026 Cultural Popup performance will serve as a major public deliverable, accompanied by open-access documentation for research and teaching. Additional outcomes include creating materials that will allow the development of both K–12 outreach workshops and curricular modules introducing students to cultural heritage, creative technology, and the ethics of AI collaboration.

### 3.3 Scholarly and Institutional Contributions

The collaboration will produce peer-reviewed articles, presentations, and conference performances linking performance studies, AI research, and ethnomusicology. Within CUNY, it strengthens and extends existing multi-campus partnerships supported by CHI’s shared digital infrastructure, positioning CUNY for larger-scale interdisciplinary collaborations and future external funding through NSF, NEH, and UNESCO programs. Another central outcome is the continued extension and integration of individual research efforts into larger meta-projects—advancing the CHI philosophy that lasting innovation arises from holistic connection across disciplines and institutions.

## 4. INNOVATION

Innovation in this project occurs simultaneously at technological, cultural, and methodological levels. Together, these dimensions redefine what interdisciplinary research can achieve when tradition and technology converge within a shared philosophical framework.

### 4.1 Technological Innovation

The project advances new systems and techniques for human–machine collaboration within live performance. Through existing CHI models, the research team will refine methods for synchronizing virtual and physical performance environments, expanding beyond existing AR/VR models toward a broader conception of combinative reality. The integration of adaptive AI systems—used in music generation, lighting, and motion control—will also produce transferable tools for blended educational and creative environments. For example, our integrated show system, QLab, can be combined with both Human and AI agents can collaborate to modify and improvise different elements of the projected and sonic cues.

4.2 Cultural Innovation
By uniting the two ensembles, the project transforms two distinct artistic legacies into a living laboratory for cultural evolution. The collaboration examines how machine intelligence can extend rather than imitate human creativity, and how traditional art forms can remain vital without losing authenticity. This approach reframes cultural heritage not as static preservation but as adaptive continuity—an evolving dialogue between historical knowledge and technological agency.

### 4.3 Methodological Innovation

At its foundation, this project demonstrates the CHI philosophy that convergent innovation lies in connection itself. The meta-project structure transforms interdisciplinarity into an ongoing process of integration, allowing discoveries in one field to inform others across an open-ended set of disciplines. By embedding this work within CHI’s existing ecosystem, the project establishes a replicable framework for large-scale, multi-campus collaboration.

Innovation here is thus not a single product, but a dynamic process: an evolving model for how human intelligence, machine intelligence, and cultural heritage can co-create new knowledge within a balanced and continuously expanding system.

## CONCLUSION

This project represents a new kind of interdisciplinary partnership—one not grounded in specific disciplinary subsets but achieved by embracing all disciplines. By linking City Tech’s expertise in technology, immersive systems, and human-machine collaboration with Queens College’s deep traditions in music and performance, the collaboration transforms two existing ensembles into a living research environment. The work honors the cultural depth of gamelan and wayang kulit while extending them into new expressive, pedagogical, and technological domains.

Using the CHI framework, our project demonstrates that convergent innovation can itself be a method of inquiry: a sustainable system in which artistic practice, technological research, and cultural study reinforce one another. The resulting performances, tools, and scholarly works will serve as models for future CUNY collaborations and for other institutions seeking to bridge cultural heritage and emerging technology.

Ultimately, this initiative seeks not only to produce knowledge, but to embody it, showing how human and machine creativity can coexist within a balanced, evolving ecosystem that honors both tradition and transformation.

# References and Citations

#### I. Foundational Frameworks & Theoretical Contexts

Balanced Blended Space. https://sites.google.com/view/balancedblendedspace/home.

Bijker, Wiebe, et al. The Social Construction of Technological Systems. 4th printing, MIT Press, 1993 (1987).

Okeefe, Brian, et al. “A Blended Space for Heritage Storytelling.” Proc. British HCI 2014, Jan. 2014, pp. 1–10. https://dl.acm.org/doi/10.1145/2593968.2593972.

Smith, David. “Collaborative AI: OER Materials for Exploring AI as a Partner Rather than a Tool.” CUNY Academic Works, Mar. 2025. https://academicworks.cuny.edu/ny_oers/77.

Smith, David B., and Ann Delilkan. “Center for Holistic Integration.” Center for Holistic Integration, https://sites.google.com/view/chi-citytech/home.

Smith, David, and Frederick Bianchi. “Balanced Blended Space: Proposing a Universal Theoretical Framework for Combinative Reality.” Publications and Research, Oct. 2023. https://academicworks.cuny.edu/ny_pubs/1239.

“EU AI Act: First Regulation on Artificial Intelligence.” European Parliament Topics, 6 Aug. 2023. https://www.europarl.europa.eu/topics/en/article/20230601STO93804/eu-ai-act-first-regulation-on-artificial-intelligence.

#### II. Cultural and Historical Foundations (Wayang Kulit and Gamelan)

Becker, Judith. Traditional Music in Modern Java: Gamelan in a Changing Society. University Press of Hawaii, 1980.

“Gamelan, Another Indonesian Tradition.” UNESCO Representative List of Intangible Cultural Heritage, https://www.unesco.org/en/articles/gamelan-another-indonesian-tradition-unesco-representative-list-intangible-cultural-heritage. Accessed 26 Sept. 2025.

“In Javanese Wayang Kulit and Contemporary Shadow Puppetry, the Medium Is the Message.” Smithsonian Center for Folklife and Cultural Heritage, https://folklife.si.edu/magazine/javanese-wayang-kulit-contemporary-shadow-puppetry. Accessed 26 Sept. 2025.

In Malaysia, Darth Vader Is Leading a Shadow Puppetry Revival. Directed by Great Big Story, YouTube, 2020. https://www.youtube.com/watch?v=7HGy2ncM010.

Sungkono, Adi Permana. “Wayang Kulit Shadow Puppetry as an Influence on Indonesian Video Game Character Design.” Paradigm Academic Press, Art and Society, vol. 4, no. 2, Feb. 2025.

“The Indonesian Art of Shadow Puppetry Sheds Light on Our New Political Reality.” Tablet Magazine, 20 Aug. 2024. https://www.tabletmag.com/sections/arts-letters/articles/american-politics-shadow-puppetry.

Wayang Puppet Theatre – UNESCO Intangible Cultural Heritage. https://ich.unesco.org/en/RL/wayang-puppet-theatre-00063. Accessed 26 Sept. 2025.

#### III. Performances, Cultural Events, and Applied Practice

An Evening of Francophone Cultura: A Cultural Event. Spring 2022. https://www.citytech.cuny.edu/humanities/news-events.aspx?id=1704.

Art + Tech: An Asian American Experience. 2 May 2023. https://www.citytech.cuny.edu/humanities/news-events.aspx?id=1689.

Delilkan, Ann. “City Tech Anti-Hate Home.” City Tech Anti-Hate Initiative, May 2024. https://sites.google.com/view/citytech-ccsd/home.

“Gamelan Yowana Sari.” Gamelan Yowana Sari Ensemble. http://www.gamelanys.com. Accessed 29 Sept. 2025.

“Gotham, Get Your Groove On – A Cultural Event.” City Tech Humanities News, 14 May 2025. https://www.citytech.cuny.edu/humanities/news-events.aspx?id=1980.

Swift, Christopher. Blended Shadow Puppet Project – A City Tech OpenLab Project Site. https://openlab.citytech.cuny.edu/wayang2024/. Accessed 6 Oct. 2025.

The MidEast: A Cultural Event. City Tech Humanities News, Feb. 2020. https://www.citytech.cuny.edu/humanities/news-events.aspx?id=1705.

Revitalizing Wayang Puppetry through Creative Lighting – PIR Journal, 3 Oct. 2023. https://pirjournal.commons.gc.cuny.edu/2023/10/03/revitalizing-wayang-puppetry-through-creative-lighting/.

“Michael Lipsey | Aaron Copland School of Music | Queens College, CUNY.” Queens College Website. https://www.qc.cuny.edu/academics/music/michael-lipsey/. Accessed 29 Sept. 2025.

#### IV. Technological and Computational Research

“Impact Soundworks – Javanese Gamelan (VST, AU, AAX) Virtual Instrument.” Impact Soundworks, https://impactsoundworks.com/product/javanese-gamelan/. Accessed 28 Jan. 2025.

Linke, Simon, et al. “Clustering of Indonesian and Western Gamelan Orchestras through Machine Learning of Performance Parameters.” arXiv:2409.03713, arXiv, 3 Sept. 2024. https://doi.org/10.48550/arXiv.2409.03713.

“(PDF) Automatic Note Generator for Javanese Gamelan Music Accompaniment Using Deep Learning.” ResearchGate, Feb. 2025. https://doi.org/10.26555/ijain.v9i2.1031.

Sen, Rego. Gamelan Sequencer (Python Project). GitHub, https://github.com/regosen/gamelan_sequencer. Accessed 27 Mar. 2024.

V. Statement of AI Use

This proposal was prepared through a collaborative writing process between the principal investigator, co-PIs, and ChatGPT-5 (OpenAI), used as a partner within the Center for Holistic Integration’s (CHI) framework of Collaborative AI. The AI system assisted in drafting, synthesizing, and editing proposal sections—including the project summary, methodology, and budget justification—under direct human supervision. Human researchers defined project goals, verified accuracy, and approved all final text. No proprietary or confidential data were shared, and the AI’s contributions were limited to language generation, structural organization, and reference support.

# Statement of Interdisciplinary Collaboration

This collaboration is rooted in CHI’s principle of Holistic Integration, which creates expansive meta-projects where disciplines converge without sacrificing their original goals. Each investigator contributes essential expertise, and the project interdependence extends across CHI’s wider ecosystem, where parallel meta-projects also feed into the deliverables described here.

David Smith (Artistic Director, CHI, City Tech) provides the overarching vision and integration framework, while also leading the design and technology implementation that enable shadow puppet performances within BSPT. He ensures the integration of this project with other active CHI meta-projects — Collaborative AI, Cultural Popup, Blended Environments, UNESCO World-Building—so that student and faculty contributions across disciplines are incorporated into the final production.

Ann Delilkan (Managing Director, CHI, City Tech) contributes cultural and managerial expertise, directing production and coordination for the Cultural Popup (Project Focus 1), while fostering partnerships across CUNY and beyond that extend the project’s impact.

Michael Lipsey (Queens College) directs Gamelan Yowana Sari, providing musical expertise, pedagogy, and cultural grounding, ensuring authentic integration of gamelan while fostering innovative extensions.

Christopher Swift (City Tech) will be director of the Blended Shadow Puppet production (Project Focus 2), and leads artistic research into Wayang Kulit design, narrative, and performance, with two CUNY Graduate Center students. Guided by advisors Dr. Claudia Orenstein and Dr. Nyoman Sedana, his team adapts dalang techniques and scenography, producing novel performance styles and scholarship.  Dr. Swift has been heavily involved in interdisciplinary education and curriculum for many years, being an early member of the City Tech Interdisciplinary Committee and creating and delivering instruction in ID courses since 2014.

# Proposed Budget

Category	Amount

1. Personnel

Research Assistant/Associates	$28,728.00

Faculty Summer salary ($15,000 cumulative maximum)	$6,942.00

Course release or reassign time	$3,979.26

Fringe benefits*	$6,339.67

Total Personnel Costs:	$45,998.93

2. Other than Personnel Services (OTPS)

Travel/Transport	$3,000.00

Supplies (itemize on separate sheet)	$9,000.00

Miscellaneous (itemize on separate sheet)	$2,000.00

Total OTPS Costs:	$14,000.00

Total Budget:	$59,988.93

*Fringe benefit rates are subject to change. Check with your college Sponsored Research office for the most recent Research Foundation fringe benefit rates.

The budget is structured to reflect a balanced partnership between City Tech and Queens College.

City Tech, through the Center for Holistic Integration (CHI), will manage all technology-based and design-driven components, including projection systems, data capture, AI integration, puppet design and preparation, puppeteers and technical crew, and documentation of blended performance experiments. Funds allocated to City Tech primarily support technical personnel, research assistants, and supplies related to stage systems, software, and recording infrastructure.

Queens College will oversee the musical and cultural performance components under the direction of Professor Michael Lipsey and Gamelan Yowana Sari, supported by Musical Coordinator Dan Cooper. Their effocovering artist coordination, rehearsal and performance expenses, and specialized instruments or materials.
Both institutions will jointly share travel, outreach planning, and documentation costs. The division of effort and expenditure ensures parity of contribution, institutional accountability, and integrated outcomes across both campuses.

# Budget Justification

Personnel – $45,998
Funds support Co-PIs Delilkan and Swift, two contract positions (Music Coordinator, Visual Artist/AI Coordinator), and student research assistants.

- Delilkan: Cultural and humanities integration; production of the Cultural Popup.

- Swift: Directs Shadow Puppet Theatre; integrates gamelan with stage and media design.

- Music Coordinator: Assists with musical arrangement, recording, and synchronization of live and digital gamelan.

- Visual Artist/AI Coordinator: Supports projection design and AI media integration.

- Student Assistants: AI testing, fabrication, projection mapping, and documentation.

- PI Smith (CHI Director) and Co-PI Lipsey (Gamelan Director) receive institutional support; no salary requested from this grant.

Fringe Benefits – per CUNY standard rates.

Supplies – $9,000
Supports expendable materials necessary for blended performance development, including projection fabrics, puppet-making materials, textiles for scenic surfaces, sensors, lighting elements, microcontrollers, cabling, and digital documentation media. These materials are essential for constructing prototypes and staging blended performances integrating gamelan, shadow puppetry, and AI-mediated systems.
Specific items will be finalized during production planning and procurement.

Travel – $3,000
Covers transportation of Gamelan Yowana Sari instruments and participating personnel between Queens College and City Tech for rehearsals, recordings, and the cultural popup performance. Includes local transport, vehicle rental, and instrument handling.

Miscellaneous – $3,000
Covers outreach and communication expenses, including printing, publicity, documentation editing, minor equipment rentals, and limited hospitality for public-facing events. May also include small fees for audiovisual licensing or repairs of instruments and staging materials.
Itemization subject to final production planning and CUNY procurement guidelines.

Total Request – $59,998
Supports interdisciplinary research, blended performance development, and public engagement through collaborative work between City Tech and Queens College.

Name: David B. Smith				Title:  Professor

Department: Entertainment Technology		College:  City Tech

Date of full-time hire at CUNY: 9-1997

Email: dsmith@citytech.cuny.edu		Telephone: 718-260-4982

Education:

College-Conservatory of Music, University of Cincinnati – Composition (D.M.A.), 1995

College-Conservatory of Music, University of Cincinnati – Music Composition (M.M.), 1981

Westminster College, New Wilmington, PA – Music Composition (B.M.), 1978

Academic and professional recognition:

U.S. Patent 6,696,631 (2004) and 7,335,833 (2008): Music Performance System

(Sinfonia®), widely deployed in professional theatrical productions, 300k+ performances

NSF TUES Grant 1141234: “Center for Performative Design and Engineering Technology” (PI), $199,820.

Composer/Sound Designer: “Dracula” –

Kevin Kline Award for Outstanding Sound Design (2007).

Composer/Sound Designer: “A Christmas Carol,” Cincinnati Playhouse in the Park –

A beloved Holiday tradition in Cincinnati for 30+ seasons.

Virtual Orchestra Design: “West Side Story” (National Tour), “Les Misérables” (West End), “Miss Saigon” (U.S. Tour), “Telecom ’99” (Lucent Technologies), “Ka”, “Love” (Cirque du Soleile).

General research history (last five years only)

13 Drivers Licenses. Documentary Film. 					2022 https://openlab.citytech.cuny.edu/13dl/. Composer for the film, which has garnered 38 international awards.

Plastic Lives.  									2023

Blended Performance for Soprano, Piano, two percussionists, dance, live video projection. I was one of three composers, designed blended technology

“Collaborative AI: OER Materials for Exploring AI as a Partner Rather than a Tool.” Open Educational Resources, Mar. 2025. COinS, https://academicworks.cuny.edu/ny_oers/77.

“Partnership and Collaboration with Generative AI in Combinative Reality.” John Jay College, https://events.govtech.com/CUNY-IT-Conference-2023.html. CUNY IT Conference 2023 John Jay College.

“Navigating Combinative Reality: Devising and Testing a Universal Framework.” Academic Series. Modul University, Vienna Austria, https://www.modul.ac.at/research/research-portal#researchseminarseries2.

“Balanced Blended Space: Proposing a Universal Theoretical Framework for Combinative Reality.” (With Dr. Frederick Bianchi) Publications and Research, Oct. 2023. COinS, https://academicworks.cuny.edu/ny_pubs/1239.

“The Archers Tale.” Blended Shadow Puppet Play. Center for Holistic Integration NYC College of Technology. May, 2024

“The Archers Tale II” Blended Shadow Puppet Play.” NYC College of Technology. May, 2025

Current Grant Activity
Co-PI in Worcester Polytechnic Institute Autonomous Vehicle Mobility Institute 2024

Leading research and development in high-fidelity, dynamic, and immersive sound environments, focusing on acoustical modeling, spatialization, and real-time audio integration for military simulation training systems.

This work is supported under the FY24 Congressional Appropriation to the Autonomous Vehicle Mobility Institute (AVMI) in collaboration with the U.S. Army Ground Vehicle Systems Center (GVSC).

Collaborators (in the past 24 months):

Dr. Frederick Bianchi, Worcester Polytechnic Institute

Dr. Christopher Swift, City Tech CUNY

Dr. Nazanin Munroe, City Tech CUNY

Dr. Ann Delilkan, City Tech CUNY

Dr. Lori McCann, Cali School of Music, Montclair State University

### Educational and Training Experience (last five years only)

Since launching the Center for Holistic Integration (CHI) in 2024, I have mentored a rapidly expanding cohort of students—3 in Spring 2024, 8 in Fall 2024, and 23 in Spring 2025—through internships, independent studies, research fellowships, and capstone projects. Many of these projects integrate directly into CHI’s ongoing meta-project ecosystem, emphasizing technical, creative, and collaborative skills in documentation and presentation.

My curriculum development experience spans over two decades, from founding City Tech’s Entertainment Technology Department, co-developing the Emerging Media Technology BTech Program and co-authoring certificates in Interactive Media and Video Production, to creating new degrees in Health Care Policy, Fashion, and Health Sciences as Dean of the School of Professional Studies. I was the founding secretary of the Colleges Interdisciplinary Committee and am on the core committee of the College’s AI Task Force.  I was one of the CUNY Building Bridges to Knowledge AI Fellows, who produced OER for the delivery of instruction in Artificial Intelligence. Current initiatives focus on Collaborative AI within Blended Space, with OER courses in Introduction to AI and Collaborative AI aligning student learning with CHI’s interdisciplinary research pipelines.

### Research Career and Current Interests

I am a composer, sound designer, and creative technologist whose 150+ sound designs and 80 compositions explore how sound and immersive environments shape human experience. At City Tech (CUNY), I founded the Department of Entertainment Technology and continue to merge the performing arts with engineering and AI research.

As Artistic Director of CHI, I advance the Balanced Blended Space (BBS) framework—modeling collaboration between human and machine intelligences—and lead projects such as the Blended Shadow Puppet Theatre and Virtual Orchestra system. My ongoing work emphasizes ethical AI integration, interdisciplinary education, and cultural innovation.

# Biographical Information

Name: Ann Delilkan			Title: Dept. Chair & Associate Professor

Dept: Humanities				College: City Tech

Date of Hire: Fall 2005			Phone: 718-260-5018

Email: adelilkan@citytech.cuny.edu

Education

Ph.D. in Linguistics. New York University. (Thesis: ‘Fusion and Other Segmental Processes in Malay: The Crucial Role of Prosody’.) 2002

Master of Arts, Linguistics. (Right-Node Rasing in English; An Optimality Theoretic Analysis of Fusion in Malay) New York University. 1994

B. Arts (Upper Class Honors), Philosophy.  National University of Singapore (Thesis: Absolutism and Relationalism: Space and Time.) 1986

Bachelor of Arts, Linguistics & Philosophy major, English Literature minor. National University of Singapore. 1985

Most recent academic/research award:

PSC-CUNY Grant Trad-A 51- 263. How productive is Nasal Substitution in Malay? Fall 2023

Professional Development/Production Management Events:

Gotham, Get your Groove on! Featuring 4 bands from divergent musical genres: Yacine Boulares’ Jazz ensemble, Taiko Masala, Samba!New York, and Dan Cooper Quartet. With Dan Cooper, music coordinator. NYCCT, May 2025.  https://www.citytech.cuny.edu/humanities/news-events.aspx?id=1980

Shedding Light: A Celebration of Asian American, Pacific Islander and Jewish Culture Funded by CUNY Anti-Hate Initiative grant, David Smith and Ann Delilkan co-PIs. Included Shadow Puppet Theatre (Christopher Swift and David Smith, with emerging media scholars), an art exhibition including artworks from across Asia--- Persia to Japan (Zhijian Qian curator), an interactive textile art exhibit (Nazanin Munroe), an interactive digital map (David Smith and Emerging Media Scholars), a student film screening (Ryoya Terao, with Entertainment Technology students) and 2 musical performances (Brooklyn Raga Massive and Taiko Masala) as well as a seminar on anti-hate activity against AAPI (Trang le Chin, coordinator) and a talk back, Kindertransport, with faculty from Hospitality Management. (Karen Goodlad, coordinator.). NYCCT, May 2024 https://www.citytech.cuny.edu/humanities/news-events.aspx?id=1970

Art and Tech: An Asian American Experience, large scale art exhibition with Koto music ensemble accompaniment, coordinated with curator Zhijian Qian. Asian artists from around NYC created and exhibited their use of technology to create interactive artworks. NYCCT, May 2023 https://www.citytech.cuny.edu/humanities/news-events.aspx?id=1689

An Evening of Francophone Culture: Fragments of Dreams and Love, in collaboration with the department of Hospitality Management and the French Consulate, and co-coordinated with Khalid Lachheb. This event featured a VR kiosk, a student art appreciation competition, bilingual poetry readings, a movie screening, a cooking demonstration, and a cheese and wine tasting. Partial funding from French Consulate.  NYCCT, March 2022 https://www.citytech.cuny.edu/humanities/news-events.aspx?id=1704

A Middle Eastern Evening: A Promenade through the Gardens with Poetry and Music, co-coordinated with Khalid Lachheb. Gnaoua Music performance (Hasan Hakmoun) and Aleppo Ensembele, with whirling dervish; bilingual poetry reading; lecture on Amazigh language; and Funded by Consulate of Morocco, NYCCT, February 2020 https://www.citytech.cuny.edu/humanities/news-events.aspx?id=1705

Cross-Cultural Practice: Recent Works by Chinese Artists in New York.   Art exhibition with traditional musical accompaniment, with curator Zhijian Qian and funded by Bank of China. May 2019 https://www.citytech.cuny.edu/humanities/news-events.aspx?id=1706

Most Recent Collaborators (Last 2 years):

David Smith, Zhijian Qian, Christopher Swift, Daniel Cooper, Nazanin Munroe, Ryoya Terao

Current Research and Work Interests:

My current work continues to focus on fostering connectivity across City Tech and beyond, to enrich the college experience of students and advance interdisciplinary research and creative activity. I am particularly committed to developing collaborations that bring together the humanities, arts, and technology to explore issues of cultural identity, representation, and social justice.

In recent years, I have coordinated and co-produced a series of large-scale, cross-cultural events that integrate music, art, performance, and digital media—each designed to encourage dialogue across disciplines and communities. These projects, such as Shedding Light: A Celebration of Asian American, Pacific Islander, and Jewish Culture (2024) and Art and Tech: An Asian American Experience (2023), reflect my ongoing interest in blending traditional cultural practices with modern media and emerging technologies.

Moving forward, I am particularly interested in extending these interdisciplinary and intercultural frameworks to collaborative research in blended performance environments, where music, digital art, and storytelling can coexist with machine intelligence and interactive design. My goal is to continue building sustainable models for collaboration—across departments, campuses, and communities—that reflect the diversity and creative potential of City Tech and the broader CUNY system.

# Biographical Information

Name: Michael Lipsey	Title: 		Professor, Assoc Chair of ACSM

Department:  Music	College:  	Queens

Date of full-time hire at CUNY: 8/2003

Email: mlipsey@qc.cuny.edu	Telephone:  	office – 718 997 3807,

home – 516 708 6936

Education:

Institution	Degree/Major	Dates Conferred

Manhattan School of Music	Masters/ Music	May 1991

Queens College	Bachelors/ Music	May 1988

Academic and professional recognition

Director, Aaron Copland School of Music, Queens College, 2019-2025

Performed with Steve Reich Ensemble, Bang on a Can, Talujon Percussion, Da Capo Chamber Players, Tan Dun.

Festivals and venues  performances –

- Lincoln Center Presents,

- Bang on a Can Summer Festival,

- PS 21 in Albany,

- Caramoor Festival,

- Royal Albert Hall (with Steve Reich and Bang on a Can),

- PKB in Denpasar, Bali with Gamelan Dharma Swara,

- La Jolla Chamber Music Festival

- the Percussive Arts Society International Convention in Nashville, Indianapolis, Austin, Texas.

General research history

Gamelan performances in Ubud/Pengosekan in Bali, Indonesia from 2010 – present.  Worked with I Ketut Dewa Alit(composer), performances in PKB 2010 and competition/performances in Ubud and Buleleng, Bali, Indonesia

Collaborators (in the past 24 months):

Recent gamelan-related collaborations -

Talujon Percussion, Theo Merigeau, I Ketut Dewa Alit, Gamelan Salukat, Gamelan Yowana Sari, Cantaloupe Records

Educational and training experience

I have been mentoring students for over 30 years.  Students of mine have been employed in orchestras in the USA and China.  They have performed with the NY Philharmonic and the Metropolitan Opera NY. A recent student of mine performed a concerto with the NY Philharmonic.  I have students that are currently employed as faculty in major universities around the world including CalArts, University of Alabama and a University in Taipei, Taiwan.

Brief narrative highlighting your research career, your current interests, and your most significant achievements

My research recently has revolved around gamelan music from Bali, Indonesia. I am working with a gamelan ensemble to help create work with Western and Balinese artists to create new works and performance opportunities.

In the last 15 years, I have formed close bonds and relationships with major artists (composers and performers) in Bali. Most of my work has been with the great Balinese musician I Ketut Dewa Alit and Gamelan Salukat.

This past summer, I took my gamelan ensemble — Gamelan Yowana Sari — to perform in Ubud and Buleleng in Bali. The performance resulted in a recording project with Cantaloupe Records. The ensemble commissioned Michael Gordon, Vivian Fung, and Evan Ziporyn to create new works for the ensemble. The release date of the CD will be February 2026 on the Cantaloupe Records label.

Going forward, I am particularly interested in how gamelan’s traditional rhythmic and timbral structures can inform new forms of cross-cultural collaboration and technology-assisted performance. I see this not only as a way to preserve cultural heritage but also as an opportunity to expand the contemporary performance landscape through dialogue between tradition, innovation, and emerging tools such as AI and interactive media.

# Biographical Information

Name: Christopher Swift	Title: Professor

Department: Humanities	College: New York City College of Technology

Date of full-time hire at CUNY: Fall, 2012

Email: cswift@citytech.cuny.edu	Telephone: 718-260-5018

Education

Ph.D., Theatre and Performance Studies, The Graduate Center, City University of New York (2012)

Certificate Programs: Medieval Studies and Renaissance Studies
Dissertation title: Theatres of Absence: Seville, 1248-1575

M.F.A., Carnegie Mellon University/Moscow Arts Theatre (1996)
Thesis: Adaptation and performance of Alexander Ostrovsky’s Diary of a Scoundrel, Teatra Tabakova

B.F.A., Theatre, Brooklyn College, CUNY (1993)

Academic and professional recognition:

Awards

Recipient of the David Bevington Award for Best New Monograph in Early Drama, 2024

Invited talks

"Shadows and Matter in Medieval Arabic Puppet Theatre.” Performing the Sacred and Profane in the Islamic World. CUNY Academy for the Humanities and Sciences. The Graduate Center, New York, NY. 2 April 2025.

“Robot Saints: What can medieval automata teach us about the age of AI?" Atlas Obscura Podcast (Oct. 17, 2023). https://www.atlasobscura.com/articles/podcast-robot-saints

Editorial board
Early Drama and Music, Medieval Institute Publications (2019-present)

General research history

Book

Ritual, Spectacle, and Theatre in Late Medieval Seville: Performing Empire. Yorkshire: ARC Humanities Press/Amsterdam University Press, 2023. (David Bevington Award, 2024)

Articles

“The Importance of Humanities in a Career-Focused Educational Environment” (with Zylstra, Belli, Cabo, MacDonald, Michals, and Sowder). In Journal of Interdisciplinary Studies in Education, vol. 13, no. 2 (2024): 61-80.

“The City Performs: An Architectural History of NYC Theater.” ArcGIS Story Map. https://arcg.is/1KHqCP (November 25, 2024).

“Sites of Performance and Circulation.” In A Cultural History of Tragedy in the Middle Ages, ed. Rebecca Bushnell, 27-48. London: Bloomsbury, 2020.

Conference Presentations

Presider and Organizer: “Dance in the Middle Ages and Early Modern Period: A Multidisciplinary Panel Honoring Lynneth Renberg’s Women, Dance and Parish Religion in England.” The 60th International Congress on Medieval Studies, Kalamazoo, Mich., May 10, 2025.

Presented paper: “New Directions for Research on Puppetry in al-Andalus,” Early European Puppetry Studies Conference, Yale University, October 12-15, 2023.

Chair: “Art in the City II,” “Community and Participation,” and “Sustainability and Resilience,” AMPS Conference: Livable Cities-New York. Brooklyn, New York. June 14-16, 2023.

Chair: “Performing the Global Middle Ages.” The 57th International Congress on Medieval Studies, Kalamazoo, Mich., Online. May 9, 2022.

Convener: “Alternative Medievalisms: Repetitions of the Medieval in Contemporary Performance,” American Society of Theatre, San Diego, Cal., October 29, 2021.

Chair: “Sustainability: Design and Theory,” “Urban Reuse,” and “Art, Literature, and Design,” AMPS Cities in a Changing World, Brooklyn, NY, June 16-18, 2021.

Presented paper: “Enduring Absences: The Architectural Semiotics of Toledo's Synagogues.” The Breath of All That Lives: New Research in Medieval Jewish Art at the 56th International Congress on Medieval Studies, Kalamazoo, Mich. Online. May 11, 2021.

Roundtable Participant: “Open Pedagogy in the Classroom: Theory and Praxis.” 2020 CUE Conference and CUNY OER Showcase. OER to Open Pedagogy: Teaching and Learning Empowered. Online. October 30, 2020.

Collaborators (in the past 24 months):

Faculty Mentor (with David Smith, Ann Delilkan, and Nazanin Monroe)

“Blended Shadow Puppets,” An Emerging Scholars Project. New York City College of Technology, CUNY, Spring 2024 and Spring 2023.

Brief narrative highlighting your research career, your current interests, and your most significant achievements:

Since the publication of my 2023 monograph on medieval Iberian performance traditions, I have been focused on the related subject of thirteenth-century Arabic shadow puppetry and entertainment technologies. In this pursuit, this past summer I conducted archival research on the topic at the Paul Kahl Archive in Turin Italy and presented a paper on my findings there at the Société Internationale pour l'étude du théâtre médiéval in Fribourg, Switzerland. The current shadow puppet proposal on Blended Shadow Puppet research and production is part of the development of performance-based approaches to historical research in shadow puppetry.

# Current and Pending Support

List of Funding Currently Available

(include no-cost extensions or start-up funds)

Title: AVMI–GVSC10-2024 Project: Sound System Modeling, Simulation and Integration in the ASL DE Ecosystem Simulator

Agency: U.S. Department of Defense — U.S. Army Ground Vehicle Systems Center (GVSC)
Funding period: 2025-26

Lead Research Organization: Autonomous Vehicle Mobility Institute (AVMI) at Worcester Polytechnic Institute

Role of faculty member:  Co-PI:

Total Award: $4,000,000 (FY24 Congressional Appropriation to AVMI)
Project Portion: Sub-award $250,000 (Co-PI; amount administered through WPI)

List of Pending Proposals

(include timelines for potential funding)

Title: AVMI–GVSC10-2025 Project: Sound System Modeling, Simulation and Integration in the ASL DE Ecosystem Simulator

Agency: U.S. Department of Defense — U.S. Army Ground Vehicle Systems Center (GVSC)
Funding period: 2026-27

Budget: $4,000,000 +

Project Portion: Sub-award $250,000 (Co-PI; amount administered through WPI)

Role of faculty member: Co-PI

Funded through a $4 million Congressional Appropriation to the U.S. Army GVSC and led by Worcester Polytechnic Institute, this multi-institutional initiative (with partners including City Tech/CHI, the University of Alabama, and VI-Grade) advances a unified digital-simulation environment for autonomous and crewed vehicles. City Tech’s $250,000 sub-award develops real-time spatial sound modeling and perceptual interfaces; the program is eligible for continued federal support for up to three additional years as benchmarks are achieved.

# List of Future Funding Prospects

### Landscape & Volatility

The current federal environment is unpredictable, and disruptions at the national level can cascade to state, city, and regranting programs. Even so, the Administration’s recent R&D priorities consistently foreground: (1) AI methods and evaluation, (2) future-computing and testbeds, (3) accessible/open research infrastructure and data, (4) workforce pathways, and (5) multi-sector collaboration. Our IRG plan is designed to produce exactly the kinds of assets that remain fundable across agencies and cycles, while pairing federal pursuits with state/city and philanthropic “stabilizers.”

## Future Funding Prospects

This IRG positions City Tech and Queens College to lead in these convergent domains by establishing a working model of human–machine collaboration grounded in cultural heritage.
The following funding sources represent next-stage opportunities enabled by the outcomes of this project:  noting that the volatility represented above may cause some, most or all of these sources to change, this list represents the type of grants and opportunities we will pursue once this situation has crystalized.

### Federal Opportunities

- NEH Humanities Research Centers on Artificial Intelligence
Up to $750,000 (3 years). Supports creation of new collaborative humanities research centers focused on societal and ethical implications of AI—ideal for expanding CHI’s human–AI collaboration model into a CUNY-wide research center.

- NSF – Human-Centered AI (HCAI) and AI Institute Programs
$1–$5 million (5 years). Funds interdisciplinary research combining computing, social science, and education. The BBS framework and blended-performance testbed could serve as a live environment for HCAI investigations.

- NSF – Cultural Heritage and Sustainability in STEM Education Initiative (IUSE Extension)
$250k–$2 million. Would extend IRG outcomes into curriculum and K–12 outreach, integrating cultural heritage with STEM learning through Collaborative AI.

- NEA – Media Arts and Performing Arts Grants
$100k–$500k. Supports technologically innovative performing arts; a clear next step for scaling public performances, residencies, and touring versions of the Blended Shadow Puppet + Gamelan collaboration.

- U.S. Department of Education – Title III Strengthening Institutions Program
$500k (annually). Could support infrastructure and digital tools for student-centered collaborative learning built on the IRG framework.

### State & City Opportunities

- CUNY Research Centers and Performance Fund – follow-on institutional support to grow the CHI ecosystem.

- New York State Council on the Arts (NYSCA) – funding for cultural performance, media art, and heritage preservation aligned with blended performance.

- New York City Department of Cultural Affairs – supports cultural education programs and public exhibitions that merge technology and heritage.

### Private and Philanthropic Foundations

- The Rockefeller Foundation – Human and Machine Creativity Initiative (emerging in 2026).

- The Ford Foundation – Technology and Society Program (equity-focused approaches to digital innovation).

- The Andrew W. Mellon Foundation – Humanities for All Times and Public Knowledge grants (for long-term institutional consortia).

- Mozilla Foundation / Knight Foundation AI and Culture Challenge (for community-driven AI experiments in the arts).

### Timeline for Grant Strategy

- Year 1 (IRG period): Develop blended-performance testbed, datasets, and outreach designs.

- Year 2: Apply for NEA and NYSCA grants (expand performances and documentation).

- Year 3: Submit proposals to NEH Humanities Research Centers on AI and NSF HCAI Programs.

- Year 4–5: Establish CHI as a CUNY-wide Center for Collaborative AI and Cultural Innovation, pursuing multi-year federal consortia funding.

### Positioning Statement

This IRG serves as a foundational phase in a multi-year funding trajectory. By delivering tangible data, interdisciplinary collaboration, and tested methodologies, the project creates the preconditions for sustained external support at federal, state, and private levels.

Vought, Russell. “M-25-34-NSTM-2-Fiscal-Year-FY-2027-Administration.” Whitehouse, 23 Sept. 2025, https://www.whitehouse.gov/wp-content/uploads/2025/09/M-25-34-NSTM-2-Fiscal-Year-FY-2027-Administration-Research-and-Development-Budget-Priorities-and-Cross-Cutting-Actions.pdf.